## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2251-swen-261-02-goated
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a HELPER I want to update my username so that I can my preferred name can be stored in the system. | **Given** I am a Helper **when** I press the update username button **then** a modal should appear to change my username | Pass | AF, 10/21/2025
| **Given** I am a Manager **when** I go to the Accounts Tab **then** nothing should appear (Specifically, a "change username" button should not appear.) | Pass | AF, 10/21/2025
As a USER I want to update my password so that I can keep my account secure. | **Given** I am a User **when** I press the update password button **then** a modal should appear to change my password | Pass | AF, 10/21/2025
As a HELPER I want to delete my account so that I can choose to no longer support or provide needs to this group. | **Given** I am a Helper **when** I press the delete account button **then** my account should be deleted (after confirmation) | Pass | AF, 10/21/2025
| **Given** I am a Manager **when** I go to the Accounts Tab **then** I should not see the delete account button | Pass | AF, 10/21/2025
As a User I want to be able to search all needs so that I can refine what I am looking to fund. | **Given** I am a User **when** I type in the search needs box **then** the list of needs on my screen should be filtered by matching what was typed in the search box | Pass | AF, 10/21/2025
As a Manager, I want to delete a need so that needs that do not need to be fulfilled can be removed from the helpers' view. | **Given** I have a need that still exists and I am a manager **when** I press the delete button **then** the need should be deleted | Pass | AF, 10/21/2025. There is no exclusively "delete" button, but a need can be deleted by removing the name via the "Edit/Delete" button.
| **Given** I am a helper **when** I go to the Needs Tab **then** the delete button should not appear | Pass | AF, 10/21/2025
As an accountless user I want to Create an Account so that I can log in and contribute to needs. | **Given** I am not logged in **when** go to the login page **then** I expect to see a create account button | Pass | AF, 10/21/2025
| **Given** I an account with the same username does not exist **when** type in my username **then** I my account will have that username. | Pass | AF, 10/21/2025
| **Given** I an account with the same username does exist **when** type in my username **then** I my account will not be created. | Pass | AF, 10/21/2025
As a User I want to be able to view all needs so that I know what I can fund. | **Given** I am a User **when** go to the Needs Tab **then** I expect to see a list of all needs | Pass | AF, 10/21/2025
As a Manager I want to be able to edit a need so that I can make sure the list of all needs is up to date with any changes made outside of the program. | Given I am a manger, When I click on a needs edit button, Then the needs edit modal should appear | Pass | AF, 10/21/2025. Again, this is done with the "Edit/Delete" button.
| Given I am a helper, When I go to the Needs Tab **then** the edit needs button should not appear | Pass | AF, 10/21/2025
As a Manager I want to Create a need so that its accessible for contribution by Helpers. | **Given** I am a manager **when** I press the create need button **then** I expect the creation modal to appear | Pass | AF, 10/21/2025
| **Given** I am a helper **when** I go to the Needs tab **then** the create need button should not appear | Pass | AF, 10/21/2025
As a Helper I want to add a need to my basket so that I can fund it later. | **Given** a need is not currently in my basket and I am a helper **when** press the Add to Basket button **then** the need should be added to my basket | Pass | AF, 10/21/2025
| **Given** a need is currently in my basket and I am a helper **when** press the Add to Basket button **then** nothing should change | Pass | AF, 10/21/2025
| **Given** I am a manager **when** go to the page that has the Add to Basket buttons (the Needs tab) **then** I should not see them | Pass | AF, 10/21/2025
As a HELPER I want to BE ABLE TO VIEW MY BASKET so that I CAN SEE WHAT I AM FUNDING. | **Given** that I am logged in as a manager **when** I open my tabs **then** I expect a basket tab to not appear. | Fail | AF, 10/21/2025. The Basket tab is visible, though clicking it will instead return the user to the Cupboard page, no matter where the user was before.
| Given that I am a helper and there are no needs in my basket, When i click on my basket, there will be no needs displayed | Pass | AF, 10/21/2025
| Given that I am a helper and there are needs in my basket, When I click on my basket, the needs in my basket will be displayed | Pass | AF, 10/21/2025
As a HELPER I want to BE ABLE TO CHECKOUT so that I CAN FUND NEEDS. | Given no needs are in my basket, When I press checkout button, an error appears | Pass | AF, 10/21/2025
| Given there are needs in my basket, When I press checkout button, all the needs in my basket get checked-out | Pass | AF, 10/21/2025
As a User I want to remove Needs from my Basket so that I can fund the Needs I want to fund. | **Given** there is a Need in my Basket **when** I click the button to remove a Need **then** the Need should be removed. | Pass | AF, 10/21/2025
| **Given** there are no Needs in my Basket **when** I try to remove a Need **then** I should receive an error. | Pass | AF, 10/21/2025. It is impossible to receive an error this way as needs can not be removed if your basket is empty.
As a USER I want to be able to log in so that I can access my account and make the changes I want to make. | **Given** I am not logged in, **when** I view the home page **then** I expect to see a button which allows me to view the log-in menu. | Fail | AF, 10/21/2025. A homepage has not been created, with the website instead sending you directly to the login page if you are not logged in.
| **Given** I am logged in, **when** I view the home page **then** I expect to see a button which allows me to view the needs page using my current saved login. | Fail | AF, 10/21/2025. A homepage has not been created, with the website instead sending you directly to the cupboard page if you are logged in.
As a USER I want to be able to log out so that others cannot access my account after I make the changes I want to make. | Given that I am logged in, when I view the Accounts page I should see a button to log out of my account. (It is not possible to view the Accounts page when logged out.) | Pass | AF, 10/21/2025